## Gantt Grid
S.No | Task | Week-1 Jul | Week-2 Jul | Week-3 Jul | Week-4 Jul | Week-1 Aug | Week-2 Aug | Week-3 Aug | Week-4 Aug | Week-1 Sep | Week-2 Sep | Week-3 Sep | Week-4 Sep | Week-1 Oct | Week-2 Oct | Week-3 Oct | Week-4 Oct | Week-1 Nov | Week-2 Nov | Week-3 Nov | Week-4 Nov
1 | Problem Identification
2 | Literature Review
3 | Requirement Analysis
4 | Dataset Selection & Collection (EXPY-TKY)
5 | System Design & Architecture
6 | Data Preprocessing & EDA
7 | Synopsis Preparation & Submission
8 | Feature Engineering & Sliding Windows
9 | Baseline Models (Hist. Avg, Linear Regression)
10 | XGBoost Model Development
11 | LSTM Model Development
12 | STGCN (Graph Model) Development
13 | Hyper-parameter Tuning
14 | Experimental Evaluation (Windows x Horizons)
15 | Backend Development (FastAPI + SQLite)
16 | Dashboard Development (Streamlit Map)
17 | Testing & Validation
18 | Research Paper Preparation
19 | Documentation & Report
20 | Final Review & Submission

## Chart Data
Task | Start Week | End Week | Start Week No. | Duration (weeks)
Problem Identification | Week-1 Jul | Week-1 Jul | 0 | 1
Literature Review | Week-1 Jul | Week-3 Jul | 0 | 3
Requirement Analysis | Week-3 Jul | Week-3 Jul | 2 | 1
Dataset Selection & Collection (EXPY-TKY) | Week-4 Jul | Week-1 Aug | 3 | 2
System Design & Architecture | Week-1 Aug | Week-2 Aug | 4 | 2
Data Preprocessing & EDA | Week-2 Aug | Week-3 Aug | 5 | 2
Synopsis Preparation & Submission | Week-3 Aug | Week-4 Aug | 6 | 2
Feature Engineering & Sliding Windows | Week-4 Aug | Week-4 Aug | 7 | 1
Baseline Models (Hist. Avg, Linear Regression) | Week-1 Sep | Week-1 Sep | 8 | 1
XGBoost Model Development | Week-1 Sep | Week-2 Sep | 8 | 2
LSTM Model Development | Week-2 Sep | Week-4 Sep | 9 | 3
STGCN (Graph Model) Development | Week-4 Sep | Week-2 Oct | 11 | 3
Hyper-parameter Tuning | Week-2 Oct | Week-2 Oct | 13 | 1
Experimental Evaluation (Windows x Horizons) | Week-2 Oct | Week-3 Oct | 13 | 2
Backend Development (FastAPI + SQLite) | Week-3 Oct | Week-4 Oct | 14 | 2
Dashboard Development (Streamlit Map) | Week-4 Oct | Week-4 Oct | 15 | 1
Testing & Validation | Week-1 Nov | Week-1 Nov | 16 | 1
Research Paper Preparation | Week-4 Oct | Week-2 Nov | 15 | 3
Documentation & Report | Week-1 Nov | Week-3 Nov | 16 | 3
Final Review & Submission | Week-3 Nov | Week-4 Nov | 18 | 2