## Jul-Nov 2026 Grid
S.No | Task | Week-1 Jul | Week-2 Jul | Week-3 Jul | Week-4 Jul | Week-1 Aug | Week-2 Aug | Week-3 Aug | Week-4 Aug | Week-1 Sep | Week-2 Sep | Week-3 Sep | Week-4 Sep | Week-1 Oct | Week-2 Oct | Week-3 Oct | Week-4 Oct | Week-1 Nov | Week-2 Nov | Week-3 Nov | Week-4 Nov
1 | Problem Identification
2 | Literature Review
3 | Requirement Analysis
4 | Dataset Selection & Collection (EXPY-TKY)
5 | System Design & Architecture
6 | Data Preprocessing & EDA
7 | Synopsis Preparation & Submission
8 | Feature Engineering & Sliding Windows
9 | Baseline Models (Historical Avg, Linear Regression)
10 | XGBoost Model Development
11 | Mid-term Review

## Jul-Nov 2026 Data
Task | Start Week No. | Duration (weeks) | End Week No. | Start Date | End Date | Start Week | End Week
Problem Identification | 0 | 2 | 2 | 2026-07-01 | 2026-07-14 | Week-1 Jul | Week-2 Jul
Literature Review | 1 | 4 | 5 | 2026-07-08 | 2026-08-07 | Week-2 Jul | Week-1 Aug
Requirement Analysis | 3 | 2 | 5 | 2026-07-22 | 2026-08-07 | Week-4 Jul | Week-1 Aug
Dataset Selection & Collection (EXPY-TKY) | 4 | 6 | 10 | 2026-08-01 | 2026-09-14 | Week-1 Aug | Week-2 Sep
System Design & Architecture | 6 | 3 | 9 | 2026-08-15 | 2026-09-07 | Week-3 Aug | Week-1 Sep
Data Preprocessing & EDA | 9 | 4 | 13 | 2026-09-08 | 2026-10-07 | Week-2 Sep | Week-1 Oct
Synopsis Preparation & Submission | 11 | 2 | 13 | 2026-09-22 | 2026-10-07 | Week-4 Sep | Week-1 Oct
Feature Engineering & Sliding Windows | 12 | 3 | 15 | 2026-10-01 | 2026-10-21 | Week-1 Oct | Week-3 Oct
Baseline Models (Historical Avg, Linear Regression) | 14 | 3 | 17 | 2026-10-15 | 2026-11-07 | Week-3 Oct | Week-1 Nov
XGBoost Model Development | 16 | 3 | 19 | 2026-11-01 | 2026-11-21 | Week-1 Nov | Week-3 Nov
Mid-term Review | 18 | 2 | 20 | 2026-11-15 | 2026-11-28 | Week-3 Nov | Week-4 Nov

## Dec 2026-Apr 2027 Grid
S.No | Task | Week-1 Dec | Week-2 Dec | Week-3 Dec | Week-4 Dec | Week-1 Jan | Week-2 Jan | Week-3 Jan | Week-4 Jan | Week-1 Feb | Week-2 Feb | Week-3 Feb | Week-4 Feb | Week-1 Mar | Week-2 Mar | Week-3 Mar | Week-4 Mar | Week-1 Apr | Week-2 Apr | Week-3 Apr | Week-4 Apr
1 | LSTM Model Development
2 | STGCN (Graph Model) Development
3 | Hyper-parameter Tuning
4 | Experimental Evaluation (Windows x Horizons)
5 | Backend Development (FastAPI + SQLite)
6 | Dashboard Development (Streamlit Map)
7 | Testing & Validation
8 | Research Paper Preparation
9 | Documentation & Thesis
10 | Final Review & Submission

## Dec 2026-Apr 2027 Data
Task | Start Week No. | Duration (weeks) | End Week No. | Start Date | End Date | Start Week | End Week
LSTM Model Development | 0 | 4 | 4 | 2026-12-01 | 2026-12-28 | Week-1 Dec | Week-4 Dec
STGCN (Graph Model) Development | 3 | 4 | 7 | 2026-12-22 | 2027-01-21 | Week-4 Dec | Week-3 Jan
Hyper-parameter Tuning | 6 | 2 | 8 | 2027-01-15 | 2027-01-28 | Week-3 Jan | Week-4 Jan
Experimental Evaluation (Windows x Horizons) | 7 | 3 | 10 | 2027-01-22 | 2027-02-14 | Week-4 Jan | Week-2 Feb
Backend Development (FastAPI + SQLite) | 9 | 2 | 11 | 2027-02-08 | 2027-02-21 | Week-2 Feb | Week-3 Feb
Dashboard Development (Streamlit Map) | 10 | 2 | 12 | 2027-02-15 | 2027-02-28 | Week-3 Feb | Week-4 Feb
Testing & Validation | 11 | 2 | 13 | 2027-02-22 | 2027-03-07 | Week-4 Feb | Week-1 Mar
Research Paper Preparation | 12 | 4 | 16 | 2027-03-01 | 2027-03-28 | Week-1 Mar | Week-4 Mar
Documentation & Thesis | 13 | 4 | 17 | 2027-03-08 | 2027-04-07 | Week-2 Mar | Week-1 Apr
Final Review & Submission | 16 | 4 | 20 | 2027-04-01 | 2027-04-28 | Week-1 Apr | Week-4 Apr